## Sheet1
Task Name | Start | End | Duration (days)
Statement of Intent | 2018-10-05 | 2018-10-12 | 7 | Preliminary Design
Brief Requirements Document | 2018-10-05 | 2018-10-17 | 12 | Preliminary Release
Class Diagram | 2018-10-17 | 2018-10-26 | 9 | Winter Break
GUI Design | 2018-10-15 | 2018-10-26 | 11 | Intermediary Release
Requirements Document (Revision) | 2018-10-27 | 2018-11-12 | 16 | Final Release
Class Diagram (First Revision) | 2018-11-05 | 2018-11-28 | 23 | Write Up
Rough Testing Strategy Plan | 2018-11-12 | 2018-11-23 | 11
Basic Functionality Prototypes | 2018-10-27 | 2018-11-28 | 32
Winter Exam Period | 2018-12-03 | 2018-12-14 | 11
Winter Break Prototyping | 2018-12-15 | 2019-01-11 | 27
Class Diagram (Second Revision) | 2019-01-14 | 2019-02-15 | 32
Finalised Testing Strategy | 2019-02-20 | 2019-03-01 | 9
Further Functionality Prototypes | 2019-01-14 | 2019-02-13 | 30
Class Diagran (Third Revision) | 2019-03-15 | 2019-03-20 | 5
Testing and Analysis | 2019-03-01 | 2019-03-20 | 19
Full Functionality Game | 2019-02-14 | 2019-03-20 | 34
Debugging | 2018-10-27 | 2019-03-20 | 144
Final Report | 2019-02-14 | 2019-03-25 | 39
Consolidation of Documentation | 2019-03-20 | 2019-03-26 | 6