## Sheet1
Task Name | Start | End | Duration (days)
Statement of Intent | 2018-10-05 | 2018-10-12 | 7 | Preliminary Design
Brief Requirements Document | 2018-10-05 | 2018-10-17 | 12 | Preliminary Release
Class Diagram | 2018-10-17 | 2018-10-26 | 9 | Winter Break
GUI Design | 2018-10-15 | 2018-10-26 | 11 | Intermediary Release
Requirements Document (Revision) | 2018-10-27 | 2018-11-12 | 16 | Final Release
JavaFX and MVC Research | 2018-11-20 | 2019-03-01 | 101 | Write Up
Rough Testing Strategy Plan | 2018-11-12 | 2018-11-23 | 11 | Research and Debugging
Basic Functionality Prototypes | 2018-10-27 | 2018-11-28 | 32
Winter Exam Period | 2018-12-03 | 2018-12-14 | 11
Winter Break Prototyping | 2018-12-15 | 2019-01-11 | 27
Finalised Testing Strategy | 2019-02-20 | 2019-03-01 | 9
Further Functionality Prototypes | 2019-01-14 | 2019-02-13 | 30
Class Diagran (Third Revision) | 2019-03-15 | 2019-03-20 | 5
Testing and Analysis | 2019-03-01 | 2019-03-20 | 19
Full Functionality Game | 2019-02-14 | 2019-03-20 | 34
Debugging | 2018-10-27 | 2019-03-20 | 144
Final Report | 2019-02-20 | 2019-03-25 | 33
Consolidation of Documentation | 2019-03-20 | 2019-03-26 | 6
NOTES
First and Second Class Diagram Revisions omitted due to to consistent evolution of development approach. Unnecessary to include intermediate class diagrams when project layout is changing frequently.
Added ongoing JavaFX and MVC Research task as a vast amount of time would go unaccounted for otherwise
Protoype deadlines pushed back to reflect the additional time that was given to the design process and also due to the added JavaFX and MVC Research task
Winter Break Prototyping represents research-driven experimentation with JavaFX and FXML, nothing tangible for the final game was produced
Final Report start date pushed back by just under a week